## Sheet1
gantt chart
topic proposal | start | End | Jan | FEB | Mar
Use Cases |  | 2021-03-13 |  | useCases
Requirenment |  | 2021-03-16 |  | requirement
SPMP |  | 2021-03-17 |  | SPMP
Tool selection |  | 2021-03-18 |  | Tool selection
Work breakdown |  | 2021-03-19 |  | Work breakdown
Gantt Chart |  | 2021-03-20 |  | Gantt Chart
Prototype |  | 2021-04-05 |  |  | create prototype
home page |  | 2021-04-06
Strategy page |  | 2021-04-07
DataBase creation |  | 04/10./21 |  |  | create database
DataBase |  | 04/10./21 |  |  | implimentstion
implimemtation |  | 04/10./21 |  |  | plug in
Plug in |  | 04/10./21
Account creation
Messaging system |  | 2021-04-19
Testing plan |  | 2021-04-22
Launch |  | 2021-04-24