## Sheet1
SPMP DATES(Milestones) | Actual Date on complition | Resaon why milestone havent met
front page 4/6/21 | 2021-04-06
slides/buttons/layers 4/10/21 | 4/20/2021-4/27/21 | last minute change. Client wants to add more info
Booking plug in 4/04/21 | 2021-04-24
product 4/20/21 | 4/20/2021-4/27/21 | client keeps on adding more product. Awaiting on prices
Payement method 4/20/21 | Awayting on client | client needs a new bank account, exploring options
creating back up 4/10/21 | TDB | still looking
requirement 3/16/21 | 2021-03-13
launch 4/23/21 | TBD- expated to be live by 4/26/21 | waitng on client to add payment method
use cases 3/13/2021 | 2021-03-13
testing plan 4/23/21(final product) |  | waitng on client to add payment method
mesaging system 4/19/21 | 2021-04-16